## Slide 1
LAUNCH PLAN · MAY 2026
Dalelis Mechanical
2.0
A 2-week plan to launch your new website and reach 4,400+ existing customers — by email and text — with your new maintenance plans.
Prepared by
FieldPass
For
James A. Dalelis, Owner

## Slide 2
THE PLAN
Three moves, one momentum.
Each builds on the last to turn your existing list into recurring revenue.
01
New website goes live
Replaces Webflow with a faster, more modern site
Same domain. Same content. Loads twice as fast and looks unmistakably like a 2026 business — not a 2018 business.
02
Maintenance plans launch
Three tiers, online payment, instant signup
Customers pick a plan, pay with a credit card, and you get the booking automatically in HousecallPro. No phone tag.
03
Email + text campaign
Reach 800 customers by email, 3,600 by text
A short, personal message from you — first by email, then by SMS to a wider list. Sent in waves to maximize replies and inbox delivery.
DALELIS MECHANICAL · LAUNCH PLAN
2

## Slide 3
PHASE 01
Your new website,
live in a day.
We've already built and tested the replacement at dalelis.vercel.app. The migration itself is a 2-hour window where we point your domain at the new site. No content is being rewritten — just delivered better.
BEFORE · WEBFLOW
✕ $30/month subscription
✕ Slow page loads
✕ No online plan signup
✕ No payment integration
✕ Looks like a 2018 site
AFTER · NEW SITE
✓ $0/month hosting (Vercel)
✓ Loads in under 2 seconds
✓ Online plan signup + payment
✓ Mobile-perfect everywhere
✓ Built-in tracking + analytics
✓ Editable text, photos, prices
DALELIS MECHANICAL · LAUNCH PLAN
3

## Slide 4
PHASE 02 · EMAIL
Reaching the people who already know you — by email.
1
Export your list
We pull all 800 customers with valid email from HousecallPro.
2
Personalize
Every email opens with their first name, signed by you.
3
Send in waves
100 per day for 8 days — keeps emails out of spam.
4
Track everything
Opens, clicks, signups — visible to you in a dashboard.
Goal: 100 emails per day → 800 customers reached in 8 days. Email goes out FIRST while SMS approval is pending in the background.
DALELIS MECHANICAL · LAUNCH PLAN
4

## Slide 5
WHAT CUSTOMERS RECEIVE · EMAIL
A short letter — not a marketing blast.
FROM: james@dalelismechanical.com
SUBJECT: Charles, a small thank-you from Dalelis
Hi Charles,
It's James — owner of Dalelis Mechanical. You've trusted us with your heating in the past, and I wanted to share something new with you before it goes public.
We just launched maintenance plans.
✓ Annual or seasonal tune-ups
✓ 10% off any repairs all year
✓ Priority emergency scheduling
✓ Plans from $19/month
See the plans →
— James A. Dalelis
WHY THIS WORKS
Personal, not promotional
Sent from your real address, addresses them by name. Looks like a letter, not an ad.
One single ask
Just one button — see the plans. Cluttered emails get sent to spam.
Direct reply works
Customers can reply and reach you, not a noreply inbox. Boosts trust and inbox placement.
Sent slowly on purpose
100/day instead of 800 at once. Avoids spam filters and warms up your sender reputation.
DALELIS MECHANICAL · LAUNCH PLAN
5

## Slide 6
PHASE 03 · TEXT
Doubling reach with a quick text.
3,600 contacts in your CRM have phones but no email — text reaches them directly.
1
Carrier approval
We register Dalelis with cell carriers (required for mass text — runs in the background, no work for you).
2
Personalize
Each text starts with the customer's first name. Identifies as Dalelis right away.
3
Send in waves
300 texts per day for 12 days. Keeps deliverability high and gives you time to handle replies.
4
Click-tracked
Every link is unique, so you see exactly who clicked and from which message.
One caveat: cell carriers require a 1-week approval for mass SMS. We submit on Day 1, send on Day 8 — runs in parallel with email so there's no idle time.
DALELIS MECHANICAL · LAUNCH PLAN
6

## Slide 7
WHAT CUSTOMERS RECEIVE · TEXT
Short, direct, identifies as you.
DALELIS MECHANICAL
Today 10:24 AM
Dalelis HVAC: Hey Charles, James here.
We just launched maintenance plans — annual HVAC tune-ups + 10% off repairs from $19/mo.
Saw our email? Take a look:
dalelismechanical.com/plans
Reply STOP to opt out.
WHY THIS WORKS
Identifies as you up front
First 12 characters say 'Dalelis HVAC:' — recipients know who it's from instantly.
Short and direct
Under 320 characters. Costs 1¢ to send and gets read in 3 seconds.
One link, click-tracked
Every recipient gets a unique URL — you'll know exactly who clicked through.
Legally compliant
Required 'STOP to opt out' is included. Sent only to customers who've called you before.
DALELIS MECHANICAL · LAUNCH PLAN
7

## Slide 8
PROJECTED RESULTS
Conservative estimates from
the first 30 days.
EMAIL · 800 CONTACTS
770
Delivered
380+
Opens (49%)
55+
Clicks
8–15
Signups
TEXT · 3,600 CONTACTS
3,500
Delivered
3,400
Read (98%)
540
Clicks
15–35
Signups
Combined: 23–50 new plan signups · estimated $9,000–$20,000 in year-one revenue
DALELIS MECHANICAL · LAUNCH PLAN
8

## Slide 9
AGGRESSIVE 14-DAY TIMELINE
From kickoff to inbox to text in two weeks.
Email starts immediately. Text approval runs in the background — no idle time.
DAYS 1–2
Foundation
Stripe goes live. We wire up payment + HCP sync. SMS carrier registration submitted (runs in background).
DAY 3
Website live
DNS cutover (2-hour window). Site goes live at dalelismechanical.com. Webflow stays running 72hr as safety net.
DAYS 4–5
Friends & family
Email goes to 50 hand-picked loyal customers first. Gather feedback. Tune the copy.
DAYS 6–10
Email campaign
100 emails per day to remaining 750 customers. Replies hit James's inbox.
DAYS 8–14
Text campaign
Carrier approval clears. 300 texts per day to 3,600 contacts. Click-tracked.
DALELIS MECHANICAL · LAUNCH PLAN
9

## Slide 10
WHAT WE NEED FROM YOU
Six small steps. ~2 hours of your time.
1
Set up a Stripe account
stripe.com — 15 min. Verify your business + bank info so we can route customer payments to you.
15 min
James
2
Export customers from HCP
Settings → Customers → Export CSV. We'll filter to email-valid and phone-valid contacts.
5 min
James
3
Sign off on email + text copy
We'll send you final drafts for approval. You can tweak any wording.
15 min
James
4
Confirm SMS carrier registration
You'll get a one-time form from Twilio asking to verify your business name + use case. Auto-filled by us.
10 min
James
5
Hand off DNS access
Whoever manages dalelismechanical.com DNS gives us 1 hour to update records.
30 min
Domain admin
6
Be on call for the launch
Day 3 cutover: be reachable so we can fix anything weird in the first hour. Usually nothing comes up.
1 hour
James
DALELIS MECHANICAL · LAUNCH PLAN
10

## Slide 11
READY?
Let's get
you a launch date.
Send back the signed-off plan and we'll kick off Day 1 the same day. Email replies hit my inbox directly — happy to walk through anything that's still unclear.
CHARLES TANANBAUM
charles@fieldpass.pro
FieldPass
DALELIS MECHANICAL · LAUNCH PLAN
11